## 2019下半年平台KR工作表
Project/Task/Responsibilities | Team Objective | To do (計劃做的) | Doing (正在做的) | Done (已經完成的) | Key Result (上線結果) | 設計師 | 前端 | PM | 備註
官網 | 官網線上申辦Design System定義，並導入inVision DSM與Zeplin提升管理效率 |  | Design System定義 |  | 1.Mockup組成效率提升百分比 2.提升與PM溝通效率 | 宗毅 | X | UED
|  |  |  | 導入inVision DSM |  | 宗毅 | X | UED
|  | Design Pattern元件化 |  |  |  | X | 婉宇 | UED
| 配合官網各專案時程，完成網頁UI/UX設計與體驗優化 |  |  | 官網-資料更新(AML) |  | 宗毅 | 婉宇 | 瑞志
|  |  |  | 蝦皮VCN啟用頁面規劃 |  | 宗毅 | 婉宇 | 仲霆
|  |  |  | VCN優化擴增快速核卡客群 |  | 宗毅 | 傑文 | 仲霆
|  |  |  | 官網新戶禮協助設計改版 |  | 宗毅 | 傑文 | 瑞志
|  |  |  | 卡企MGM活動(切版中) |  | 宗毅 | 婉宇 | 仲霆 | 進行中，8月底以前完成，9月進IT開發
|  | OPEN ApI串接&未來SSO身分驗證中心調整 |  | OPEN ApI串接&未來SSO身分驗證中心 |  | 宗毅 | 婉宇 | 冠瑢 | 確認中
|  |  |  | 分期預借現金免審核 |  | 宗毅 | 婉宇 | 仲霆 | 10/14進開發
|  |  |  | 紅利點數預約折抵服務(切版中) |  | 宗毅 | 傑文 | 仲霆 | 9/25 refine，10/14進開發
|  |  |  | 分期同意書流程優化 |  | x | 婉宇 | 仲霆 | 10/18完成
|  |  | Apin簡訊結果頁優化-強化MMB |  |  | 宜萍 | 傑文 | 佩璇
|  |  | 資料更新英文版 |  |  | 宜萍 | 婉宇 | 瑞志 | 10月底交付
|  | CRS資料更新 |  |  |  | 宜萍 | 婉宇 | 瑞志 | 2020 1月開發
|  | 長榮登入活動切版 |  |  |  | 宗毅 | 傑文 | 瑞志 | 10月中進開發
|  |  | 官網預約諮詢信託(等切版) |  |  | 欣儒 | 婉宇 | 舒涵 | 畫面已完成
| 官網線上申辦各項服務NPS滿意度提升 |  | 線上申辦(上傳優化) |  | 1.線上申辦NPS維持70分以上 2.MyBill NPS提升(3/8-5/8) 61分 | 宗毅 | 婉宇 | 仲霆
|  | MyBill新增記憶信用卡號功能 |  |  |  | 宗毅 | 婉宇 | 仲霆 | 8/1與PM過流程UX，PM會再調整流程規劃
|  | 增加Qrcode上傳文件 |  |  |  | 欣儒 | 婉宇 | 仲霆
|  |  | 官網線上申辦NPS改版 |  |  | 欣儒 | 婉宇 | 瑞志 | 設計樣式已確認，待婉宇排入切版
|  |  | 線上申辦設計元件美化 |  |  | 欣儒 | 婉宇 | 仲霆
|  |  |  | 信用卡NPS線上申辦優化 |  | 欣儒 | 婉宇 | 仲霆
|  |  |  | 線上申辦引導MMB下載優化 |  | 欣儒 | 婉宇 | 仲霆
|  |  |  | 線上申辦姓名欄位改200字元 |  | 宗毅 | 傑文 | 舒涵 | 進行中，7月底要提供
|  |  |  | SurveyCake問券結果頁 |  | 宗毅 | 傑文 | 姿伶/David
| 官網Design System導入inVision DSM與Zeplin，提升管理與協作效率 |  | Design System整理與定義 |  | 1.Mockup組成效率提升百分比 2.提升與PM溝通效率 | 欣儒 | 婉宇 | UED
|  |  | 導入inVision DSM |  |  | 欣儒 | Ｘ | UED
| 官網數位專區網頁設計，提升用戶對於數位產品的了解 |  |  | 資訊架構釐清 | 1.數位產品引導Action點擊量 2.數位專區瀏覽量(預計10萬/月) | 欣儒 | 婉宇 | 舒涵
|  |  | 首頁主頁網頁設計 | [5 empty] | 8/30和PM過首頁設計風格討論
|  | 學生客群情境網頁 | [6 empty] | https://airtable.com/shrO6dypLsvkh08go/tblzgFqQaaM4aM33E?blocks=hide
|  |  | 上班族情境網頁 | [5 empty] | https://whimsical.com/BhsghSxs2N6CuuELSDCY2x#7YNFXnKbZAGB2NE6sjHSv
家庭主婦情境網頁
成家立業情境網頁
退休情境網頁
| 官網首頁改版 |  |  | 新官網mega menu CMS上稿所需ICON圖檔製作，預告燈箱 | 1.提升官網首頁數位產品引導Action點擊量 | 欣儒 | 傑文 | 舒涵
| 官網效能提升 |  | 行動版首頁 |  | Google Speed效能檢測PC 90分以上，Mobile 70分以上 | Ｘ | 傑文/婉宇 | 舒涵 | 9/25一起修正測試
平台行銷 | 數位平台行銷外包網頁設計品質檢視與效能提升，協助提升平台推廣效益 |  |  | 保險網站效能優化 | Google Speed效能檢測PC 90分以上，Mobile 70分以上 | X | 婉宇 | 行銷
|  |  |  | 貸就補網頁效能優化 |  | X | 婉宇 | 行銷
|  |  |  | 外包網銀說明網頁設計檢視 |  | 欣儒 | X | 行銷
|  |  |  | 外包無現金活動網頁設計檢視 |  | 欣儒 | X | 行銷
|  |  |  | 信用卡通路新增MMB下載廣告(電子帳單、實體帳單、消費彙整通知等...) | 提升MMB下載引導Action點擊量 | 欣儒 | x | 鈞堯 | 會設計兩種版本做成效A/B testing
|  |  |  | EDM規範網站新增行動銀行的連結 |  | 淨祺 | x | 鈞堯
|  |  |  | 行動銀行APP MGM活動行銷公版與廣宣banner |  | 欣儒 | x | 鈞堯
|  |  |  | 行動銀行APP MGM活動捷運燈箱行銷廣宣 |  | 欣儒 | x | 鈞堯
戰情室 | 配合戰情室各專案時程，完成網頁UI/UX設計與體驗優化 |  |  | 官網_台灣之星專案引導頁 |  | 宗毅 | 婉宇 | David
|  |  |  | 線上開戶第一階段(測試調整) |  | 淨祺 | 傑文 | 君楷 | 上傳頁面8/7有優化修正
|  |  |  | 線上開戶第二階段優化 |  | 淨祺 | 傑文 | 君楷 | 9月中完成
|  |  |  | 信貸試算優化 |  | Ｘ | 傑文 | David
|  |  | 線上預約開戶通知信 | 線上預約開戶小調整 |  | 宜萍 | 傑文 | 君楷
|  |  | 二胎房貸 |  |  | 欣儒 | 傑文 | David | 10/2官網refine，10/14~10/25製作設計稿，10/28~11/1設計稿確認與調整，11/4~11/15製作切版
|  | Pinkoi電商貸 |  |  |  | X | 婉宇 | 少淳
網銀 | 網銀系統介面優化，提升瀏覽體驗與官網一致 |  |  | 網銀首頁改版 |  | 淨祺 | 傑文 | 佳宜 | 切版已給架構，剩下IE微修正
我的最愛ICON繪製與頁面設計
|  |  |  | 網銀-資料更新 | 1.網銀整體NPS提升 2.網銀登入後首頁預計10月上線 3.無障礙官網徽章A申請 | 宗毅 | 傑文 | 佳宜
|  |  |  | RWD Table樣式設計 |  | Ｘ | 傑文 | UED
|  |  |  | 無障礙網銀 |  | Ｘ | 婉宇 | 瑞志
|  |  |  | Cpin申辦結果頁導MMB申辦 |  | 欣儒 | 婉宇
|  | 網銀登入後Design System整理 |  |  |  | 新人 | 傑文 | UED
MyATM | MyATM網站介面與資訊架構改版，協助將客戶導流其他數位服務 |  |  | 首頁與登入 | 1.其他數位產品引導Action點擊量 2.MyATM瀏覽量提升 | 宗毅 | 傑文 | 陳旻 | 8/12以前要確認首頁與登入頁設計，給傑文切版
功能選單
我的常用帳號
轉入約定帳號
轉入其它帳號
餘額查詢畫面
帳戶交易明細畫面
MyMemo轉出明細
常用帳戶設定畫面
個人資料設定畫面
網銀密碼畫面(待切版)
變更晶片卡密碼
|  |  |  | MyATM交易通知信 |  |  |  |  | 9/23通知信待PM整理資料與項目
LINE BC | LINE BC個人化服務介面流程與行銷視覺設計，協助提升用戶體驗與綁定人數 |  |  | 夏季風圖卡設計 | 1.LINE BC綁定人數提升 2.新功能使用人數提升 3.LINE BC NPS問券結果 | 欣儒 | Ｘ | 逸慧
LINE BC主題背景-ROBO慶生
秋季風圖卡設計
|  |  |  | LINE BC串接MyBill驗身-介面流程介面圖設計 |  |  | Ｘ |  | 7/31交付
|  |  |  | LINE BC設定繳費提醒-介面流程與卡片設計 |  |  | 婉宇 |  | 8月中(暫定)交付
|  |  | 主選單加入ROBO慶生主題 |  |  |  | X
|  |  | 主選單加入MMB主題 |  |  |  | X
|  | LINE BC介面優化(第一階段) |  |  |  |  | 婉宇
|  | LINE BC介面優化(第二階段) |  |  |  |  | 婉宇
通知信 | 交易通知信版型管理與測試，提升郵件瀏覽體驗 |  |  | 行動銀行登入通知信改版並導入Billhunter | 1.通知信導入系統比例提升 2.通知信引導點擊量提升 | 宗毅 | 婉宇 | David | 切版完成，待上MMB IT套版
|  |  |  | 阿發Email交易通知信版型設計需求 |  | 宗毅/致儒 | 婉宇 | David | 已完成
|  |  |  | 官網KYC完成通知信 |  | 宗毅 | 婉宇 | 瑞志 | 已完成
|  |  |  | G0499【e-TABS系統】授信提前還本交易彙整通知 |  | 宗毅 | X | David | 8/2以前完成版型建立
|  |  |  | G0399【OnDemand報表】 貸款額度到期前4個月通知清單 |  | 宗毅 | X | David | 8/2以前完成版型建立
|  |  |  | Cpin申請網銀密碼新增通知信 |  | 宗毅 | x | 江lulu | 8/15仍確認中
|  |  |  | NGU99【國泰世華銀行】客戶資料更新通知 |  | 宗毅 | X | David | 已完成
|  |  |  | Quick Cash專案通知信 |  | 宗毅 | X | 周欣威 | 電聯單6000010811362，企網銀通知信
|  |  |  | 網銀金融卡開卡通知信 |  | x | 婉宇 | 慶庭 | 預計10/7完成
|  | 繳款入帳彙整通知 |  |  |  | x | 婉宇 | 佳均
|  | 還款繳息通知信 |  |  |  | x | 婉宇 | 冠瑢
|  |  |  | NGV99【國泰世華銀行】個人基本資料更新通知 |  | 宗毅 | X | David | 已完成
|  |  |  | 信用卡消費彙整通知欄位調整-新增國外交易手續費 |  | x | 婉宇 | 欣珮 | 已完成
|  | ROBO通知信導入系統 |  |  |  | 阿邵 | 婉宇 | 盈蒨
|  | ROBO投資月報 |  |  |  | 阿邵 | 婉宇 | 盈蒨
KOKO、ROBO | 配合KOKO、ROBO各專案時程，完成網頁前端開發需求 |  |  | KOKO官網旅綜險切版(剩下試算) |  | 致儒 | 婉宇 | KOKO | 8/1上線，後續製作試算
|  |  |  | ROBO首頁“看看別人怎麼買”資料帶出效果製作 |  | 阿邵 | 傑文 | 盈蒨 | 預計7/31提供程式範例給阿邵套入
|  |  |  | ROBO試算調整 |  | x | 傑文 | 盈蒨
|  |  |  | ROBO header增加小紅點 |  | x | 傑文 | 盈蒨 | 8/26提供
其他 |  |  | 收單紙捲列印規格 |  |  | 宜萍 | x | 佩璇

## LINE BC專案時程
LINE BC介面美化
網址開頭 | 功能 | 頁數 | 優先調整
A | 個人化服務綁定 | 6 | V
B | 訊息通知 | 6 | V
C | 信用卡帳務 | 8
D | 紅利點數 | 1
E | 刷卡優惠 | 1
F | 錯誤/轉導頁面 | 10 | V
G | 無卡提款 | 3
H | 無卡提款(查詢頁) | 1
I | 無卡提款(未啟用) | 1
J | 優惠券 | 4
| 繳費 | 1 | V
項目 | 需求文件 | 預計上線日 | 期望交付日
LINEBC串接MyBill驗身 | 附件P1~6 | 2019-08-16 | 2019-07-31
LINEBC設定繳費提醒 | 附件P7~9 | 9月中(暫定) | 8月中(暫定)

## 官網數位專區時程
項目 | 單元 | 內容 | 完成日期 | 狀態 | 人員 | 備註
提案企劃 | 首頁 | 風格討論 | 2019-07-11 | 已完成 | 淨祺/欣儒/婉宇/舒涵
提案企劃 | 首頁 | 文案調整 | 2019-07-15 | 已完成 | 舒涵
提案企劃 | 首頁 | 設計初稿 | 2019-07-19 | 已完成 | 欣儒 | 先出搭配文案的一版
提案企劃 | 首頁 | 設計review | 2019-07-19 | 已完成 | 淨祺/欣儒/婉宇/舒涵 | 下午討論
提案企劃 | 首頁 | 設計二稿review | 2019-07-22 | 進行中 | 淨祺/欣儒/婉宇/舒涵
首頁
提案企劃 | 內頁-線上申辦信用卡 | 文案初稿 | 2019-07-18 |  | 舒涵
提案企劃 | 內頁-線上申辦信用卡 | 架構討論 | 2019-07-19 |  | 淨祺/欣儒/婉宇/舒涵
提案企劃 | 內頁-線上申辦信用卡 | 設計初稿 | 2019-07-23 |  | 欣儒
提案企劃 | 內頁-線上申辦信用卡 | 設計review | 2019-07-24 |  | 淨祺/欣儒/婉宇/舒涵
提案企劃 | 內頁-線上申辦信用卡 | 報告Lisa | 2019-07-26 |  | 淨祺/欣儒/婉宇/舒涵 | 下午
內頁-線上申辦信用卡
內頁-線上申辦信用卡
提案企劃 | 內頁-網路銀行/MMB | 文案初稿 | 2019-07-18 |  | 舒涵
提案企劃 | 內頁-網路銀行/MMB | 架構討論 | 2019-07-19 |  | 淨祺/欣儒/婉宇/舒涵
提案企劃 | 內頁-網路銀行/MMB | 設計初稿 |  |  | 欣儒
提案企劃 | 內頁-網路銀行/MMB | 設計review |  |  | 淨祺/欣儒/婉宇/舒涵
提案企劃 | 總報告 | 報告Quincy | 2019-08-05 |  |  | PO會議報告

## Conv Strategy (hidden)
Group | Accounts | Action | Letter Type
Installment accounts | 6M | To be converted with sales finance | N/A
Associates: M2+, Blocked, Closed, Disputes | 21M | Associates terminates | (A) Termination letter in Associates letterhead
Associates: M1 | 6M | Contional conversion: automatic conversion if account brought to current by deadline; if not, Associates terminates account | (B) Conditional conversion letters with negative option in joint letterhead
Associates current w/o Citi | 107M | Automatic conversion | (C) Automatic conversion letters with negative option in joint letterhead
Associates current and Citi current | 22M | Automatic conversion | (C) Automatic conversion letters with negative option in joint letterhead
Associates current and Citi M1 | 415 | Automatic conversion | (C) Automatic conversion letters with negative option in joint letterhead
Associates current and Citi M2 | 45 | Automatic conversion | (C) Automatic conversion letters with negative option in joint letterhead
Associates current and Citi M3+ | 217 | Associates terminates | (A) Termination letter in Associates letterhead
Associates current and Citi W/O | 31 | Associates terminates | (A) Termination letter in Associates letterhead
Associates current and Citi blocked | 1M | Associates terminates | (A) Termination letter in Associates letterhead
As of April , 2001. By Marketing

## Operation activities (hidden)
Item No. | Tasks/Activities | Deliverables | Dependencies/ Source/ Approval | Owner | Status | Target Complete Date | Actual Complete Date | Meeting/Doc/ Ref. | Conv. Task Ref.
1.0 | Compliance Assurance
1.1 | Ensure the requisite archival compliance of conversion programs and databases in Citi, Aries and EDS. | QA confirmation = 2 year | QA comment | Tech | Done | 4/2 | 2001-05-09
1.2 | Obtain"endorsement" of data transport from site to site on physical media | Confirmation | BISO/GISO comment | James/Tech. | Done | 4/6 | 2001-04-23
1.3 | Ensure the requisite archival compliance of conversion programs and databases in ITO. | Requisite retention: at least 1 year after conversion cut-over |  | Sheue Ling/ITO | Done | 3/23 | 3/23
1.4 | Ensure the requisite record retention compliance viz. Application documentation, signature, etc. | Follow BAU |  | TSG | Done | 4/2 | 4/2
1.5 | Ensure the form of original application forms archive is compliant (image or hardcopy). | QA comment | QA | TSG | Done | 3/12 | 3/12
1.6 | Ensure the size of sampling check is compliant. | QA comment | QA | Tech | Done | 3/12 | 3/12
1.7 | Confirm if Citi can undertake collection action on behalf of BOOC (SLA, License, etc.) | Confirmation | Confirmation | Betty/Sam | Done | 2001-04-03 | 2001-04-04
1.8 | Confirm with QA for issues related to reconciliation procedures (eg. Online vs. hardcopy, sampling size, temp staff … etc) | QA comment | QA | Tech | Done | 2001-04-20 | 2001-04-24 | 4/17-18
1.9 | Revise communication later according to 4/18 the change of address mapping for dual w/Citi customers (Citi add will be applied). | Revised communication letter | Approved by SAM. | Mkting | Done | 2001-04-20 | 1901-02-23 | 4/17-18
1.10 | MOF Approval | Approval |  | Betty | Done | 2001-04-19 | 2001-04-25
1.11 | Confirm legal view on cancelling 3-day grace period | SAM's comment, Betty's recap |  | Amy | Done | 2001-04-23 | 2001-04-25
1.12 | Consult Frau in finding a solution regarding JCIC reporting, to avoid negative impact to cusomer's JCIC record if grace period is cancelled. | Instruction from Ward |  | Amy | Done | 2001-04-23 | 2001-04-25
1.13 | Confirm "negative check" on reconciliation of mailing is compliant | QA comment |  | Vincent | Done | 2001-04-23 | 2001-04-24
1.14 | Confirm if Citibank's contract with Jardines Salmat enable us to print labels for Associates | Confirmation |  | Jerry | Done | 2001-04-27 | 2001-04-26 | 4/24 Sam's comment
1.15 | Confirm legal status of transferring converted customer's insurance payment | Confirmation - stated in notice letter |  | Wen | Done | 2001-05-21 | 2001-05-22 | 5/18 tele-con
1.5 | Aires product mapping
1.51 | Installment (EPP + ALOP)
Balcon
Insurance by Credit Card
Differentiate APR
Automatic Cash Pin/Tpin / Internet Pin Mailer to customer who has pin in Aries??
Automatic GPP flag conversion??
EDS download customer list who registered Autopay / Utility / Insurance…
Is the conversion strategy for active and inactive accounts the same??
Aries Golfer card
Get BOOC card embossing format for OLA feasibility study for Areis card support
Contact HSM vendor to ensure no issue for Aries CVV key loading
2.0 | Conversion and Balcon Scope/Algorithm
| Determine biz conversion strategy - JCB / Ucard - single / multiple cards ; single / dual accounts - Active/inactive/bad accounts | - Discontinue JCB and Ucard - Treat JCB as Visa or MC?? In conversion. |  | Marketing
| Historical txn txn code mapping | Historical txn can only be converted to ECS after account creation. |  | DM/Fincon/TSG
| Balance xfer strategy - EDS provides after batch details like min. due, txn details and outstanding balance. However, ECS only accept min. due and outstand balance for batch process. Txn details will not be processed in batch but shown in PCSD. - ECS been informed by EDS data for deliquency status on cycle date. | Citibank statement only showed BOOC outstanding balance amount instead of txn details in statement. |  | ITO/team
| BOOC to ECS EPP / ALOP / Balcon / POT table mapping |  |  | Marketing
2.1 | Estimate # of Qalified CIF | # of CIF |  | RM | Done | 3/17 | 3/17
2.2 | Determine treatment for dispute a/c's |  |  | Marketing | Done | 3/21 | 3/21
2.3 | Define criteria for Qualified | Criteria |  | RM | Done | 3/9 | 3/9
2.4 | Determine credit limit offer for the qualified | User requirement |  | RM | Done | 3/9 | 3/9
2.5 | Determine treatment for cash rebates | User requirement |  | Marketing | Done | 3/9 | 3/9
2.6 | Provide the name list of dual relationships which perform unsatisfactorily at Citi | Name list |  | RM | Done | 3/23 | 3/23
2.7 | Notification Letter mailed out for (2.6) a/cs | Letter mailing | 2.6 | BOOC | Done | 3/28 | 3/28
2.8 | Close (2.6) BOOC accounts | A/C Closed | 2.7 | BOOC | Done | 2001-03-28 | 2001-03-28
2.9 | Determine treatment for credit balances - whether to BALCON | Decision: convert. (RCC: upload in Nixdorf format) |  | Betty/TSG | Done | 3/29 | 3/29
2.10 | Categorization of customers and actions | User requirement |  | RM | Done | 3/9 | 3/9
2.11 | Define the scope of a/c to be fed into RMS (or to sell out?) | 1) 100% coverage of customer base 2) Different cuts, overlaps, e.g. Blocked & M2, what is in Blocked 3) Blanaces in each category 4) Precise actions to be taken, e.g. what is "close" 5) Weekly report until transition launch |  | Credit Op. | Cancelled | 4/6 | N/A | 4/12 Workshop
2.12 | Determine the length of tracking period for M2+ |  | 2.11 | Credit Op. | Cancelled | 3/26 | N/A | 4/12 Workshop
2.13 | Decide whether to outsource M2+ |  | 2.11 | Credit Op. | Cancelled | 3/26 | N/A | 4/12 Workshop
2.14 | Explore feasibility of deferred card activation |  |  | RCC | Done | 3/9 | 2001-03-15
2.15 | Determine the stop point of BOOC new cards solicitation |  | Marketing's decision whether to employ BOOC's sales agents | Marketing | Done | 3/12 | 2001-03-12
2.18 | Confirm the letter mailing process for M1 (separate after 1 month?) |  |  | Marketing | Done | 3/21 | 2001-03-23
2.19 | Confirm "Balcon+Block" or "Balcon, no block and OTB restriction." | Mgmt decision: Issue card earlier; Activate & Block, Balcon and Block. |  | Betty | Done | 3/21 | 2001-03-21
2.20 | Determine how long we need to keep JOCS operating. | Decision: Upon Installment accounts' closure |  | Team | Done | 3/23 | 3/23
2.21 | Confirm how far back are voluntary attrited a/c's captured? | Answer: since Day 1 |  | BOOC | Done | 3/23 | 3/23
2.22 | Confirm how far back are closed a/c's captured? | Answer: since Day 1 |  | BOOC | Done | 3/23 | 3/23
2.23 | Compile a "Communication List" that gives details of communication materials at all phases. | Communication List |  | Marketing | Done | 4/3 | 2001-04-04
2.24 | Finalize letter content | Agreed: no FAX number provided; only accept mail return |  | Marketing | Done | 3/23 | 3/23
2.25 | Provide a written confirmation of selection criteria to Telly |  |  | Erica/RM | Done | 2001-04-17 | 2001-04-17 | 4/17-18 meeting
2.26 | Confirm exact date of freezing database | Confirmation from Erica (8days prior to mailing out) |  | RM & Marketing | Done | 2001-04-23 | 2001-04-23
2.27 | Confirm whether to book into JOCS the 104 new applications approved after 4/25. |  |  | RM | Done | 2001-05-07 | 2001-05-07 | 5/4 tele-con
2.28 | Provide a break-down by types of the 104 new applications |  |  | Telly/Associates | Cancelled (Erica) | 2001-05-07 |  | 5/4 tele-con
2.29 | Provide a plan of how the installment accont will be handled. |  |  | Wen | Cancelled (ref to task force run by Jim Brown)
3.0 | BOOC Equipment and Premises
3.1 | Review BOOC fix assets/hardware to determine continue employment or write-off. | Review result (4/16 Aftab mail) |  | Tech | Done | 4/6 | 2001-04-16
3.2 | Identify redeployable vs. not redeployable PCs | Inventory list |  | Tech/CGTI | Done | 2001-04-17 | 2001-04-26 | 4/16 Aftab mail
3.3 | Coordinate users to identify redeployable printers and fax machines. | Fix asset list |  | Tech/CRS | Done | 2001-04-17 | 2001-04-26 | 4/16 Aftab mail
3.4 | Develop redeploy plan for PCs, Servers, printers and fax machines. | Redeploy plan |  | ACC/GPS/CRS | Cancel (see 3.9) | 2001-04-17 | 2001-04-26 | 4/16 Aftab mail
3.5 | Determine arrangement for two PBX, Nortel and Lucent. | Deployment plan |  | CGTI | Cancel (see 3.9) | 2001-04-17 |  | 4/16 Aftab mail
3.6 | Provide backgrounds of the decision not using the Switch and Hub. | Explanation (by CL) |  | Tech | Done | 2001-04-17 | 2001-04-17 | 4/16 Aftab mail
3.7 | Arrange Leigh Mardon to make investment (purchase or long-term lease) on the Embossing machine or, seek for other buyer. | Decision |  | Vincent/TSG (passed to GPS) | Close (case f/u by GPS) | 2001-05-11 | 2001-06-18 | 4/16 Aftab mail
3.8 | Adjust book value, estimate the depreciation expense, budget the maintenance cost ..etc. |  |  | Fincon | Done |  | 2001-06-04 | 4/16 Aftab mail
3.9 | Develop an inventory management process for all equipment that will be transferred. | Inventory Management Process |  | Fincon | Done |  | 2001-05-15
4.0 | EDS/JOCS Charge Scheme
4.1 | Review EDS contract |  |  | Tech | Done | 4/6 | 2001-04-19
4.2 | To finalized contract sign-off with EDS |  |  | James & Associates | Done |  | 2001-06-01
5.0 | Capacity Plan/Arrangement
5.01 | APPC systems/network capacity plan evaluation |  |  | ITO
5.02 | Technology local systems/servers capacity plan evaluation |  |  | Technology/Citibank
5.1 | FTE Requirement - Citiphone | FTE Requirement |  | Citiphone | Done | 3/8 | 3/8
5.2 | Budget Requirement - Citiphone | Budget Requirement | 2.1 | Citiphone | Done | 3/8 | 3/8
5.3 | FTE Requirement - TSG | FTE Requirement | Robert Matthews & Shariq | TSG | Done | 3/26 | 3/26
5.4 | Budget Requirement - TSG: - Imaging the old account's applications | Budget Requirement | 2.1 | TSG | Done | 3/26 | 3/26
5.5 | Budget Requirement - TSG: - One-time statement send-out for old accounts | Budget Requirement | Collection/Markteing | TSG | Done | 3/26 | 3/26
5.6 | Budget Requirement - TSG: - Embossing machine capacity | Budget Requirement | Marketing / legal | TSG | Done | 3/26 | 3/26
5.7 | Budget Requirement - TSG: - Plastic card stocks for 150,000 | Budget Requirement | Marketing/LM | TSG | Done | 3/26 | 3/26
5.8 | Budget Requirement - TSG: - Conversion Verification Test FTE and expense | Budget Requirement |  | TSG | Done | 3/26 | 3/26
5.9 | Budget Requirement - TSG: - C/H payment transaction fee | Budget Requirement | Sample % | TSG | Done | 3/26 | 3/26
5.10 | Budget Requirement - TSG: - Balcon manual effort once RCC could not support. | Budget Requirement | Accounts | TSG | Done | 3/26 | 3/26
5.11 | Budget Requirement - TSG: - PSP and OOE for extra H/Cs | Budget Requirement | RCC | TSG | Done | 3/26 | 3/26
5.12 | Recruit Associates Candidates- Citiphone |  | HR | Citiphone | Done | 2001-04-12 | 2001-04-09
5.13 | Seat Planning (Hotelling Feasibility Study)- Citiphone |  | Citiphone | Citiphone | Done | 3/22 | 3/22
5.14 | Incremental Equipment (PC, phone set, etc.)- Citiphone |  | Citiphone | Citiphone | Done | 3/12 | 3/12
5.15 | Capacity Plan for handling referrals (due to activate/block) - Auth | Capacity plan |  | Auth | Cancelled (see 6.1) | 4/6 | N/A
5.16 | Capacity Plan for handling referrals (due to activate/block) - Citiphone | Capacity plan |  | Citiphone | Done | 3/23 | 3/23
5.17 | Arrange for Leigh Mardon’s visit to Associates again to assess usability of one of their embossing machines and cycle time. |  |  | TSG | Done | 3/30 | 3/30
5.18 | Produce an action plan to relocate to Leigh Mardon’s site as well as seeking an on-loan unit from the hardware vendor. |  |  | TSG | Cancelled (see 3.7) | 3/30 | N/A
5.19 | Obtain written confirmation from Jardin & LM regarding statement printing /card embossing capacity | Jardin Salmat: contract Leigh Mardon: |  | TSG | Done | 3/26 | 2001-05-04
5.20 | Confirm with QA if the expected card storage (time span) is compliant | QA comment = no specific issue |  | TSG | Done | 4/6 | 4/6
5.21 | Provide a list of JOCS files and data volume, for back-up volume estimation | List of file and volume |  | Francis/Associates |  | 2001-05-10 |  | 4/17,18 meeting
5.22 | Specify which files to back up from JOCS (full or master files only?) | Decision: full back-up |  | RCC & Tech | Done | 2001-04-20 | 2001-04-26 | 4/17,18 meeting
5.23 | Find out solution for reconciliation report printing - 1) storage availability for print-outs 2) approval for deviation for using soft-copies? | Hardcopy will be printed by Citi datacenter. |  | Tech | Done | 2001-04-20 | 2001-04-26 | 4/12 meeting
5.24 | Compile a security handling procedure for the large volume embossed cards. | Procedure |  | Vincent Chen | Done | 2001-05-08 | 2001-05-16 | 4/27 O&T meeting
6.0 | Operation Process Design
6.1 | Produce customer service plan during the conversion period- Auth | Call triggers, anticipated volume, time-frame, script, responses, system support, capacity |  | Auth | Done | 4/6 | 2001-04-27
6.2 | Produce customer service plan during the conversion period- Citiphone | Call triggers, anticipated volume, time-frame, script, responses, system support, capacity |  | Ciitphone | Done | 4/6 | 2001-04-20
6.3 | Reconcilement framework | Task List |  | Tech/User | Done | 3/26 | 2001-04-18 | 4/17,18 meeting
6.4 | Returned mail handling process | Decision: BOOC mark as "negative responded." |  | BOOC | Done | 3/23 | 3/23
6.5 | Payment process - for payment made during and after the transition before all a/c's on JOCS are cleaned up |  |  | TSG | Done (BAU) | 2001-03-23 | 2001-03-23
6.6 | Confirm who will follow up maintenance of addresss deviation (based on exception report) |  |  | Team | Cancelled | N/A | N/A | 4/17,18 meeting
6.7 | Develop a generic reconciliation form | Reconciliation form |  | Amy | Done | 2001-04-23 | 2001-04-26 | 4/17,18 meeting | 1.0
6.8 | Confirm if the new added field (convert flag) will be inccluded in the master file layout provided. | Confirmation = yes |  | Francis/Associates | Done | 2001-06-01 | 2001-04-20 | 4/17,18 meeting | 1.2
6.9 | Confirm which report for CPO to reconcile conversion accounts | Report name |  | Jack | Cancelled(Tech gen rpt) | 2001-04-23 | N/A | 4/17,18 meeting | 3.3
6.10 | Complete reconciliation procedure. | Reconciliation procedure |  | TSG | Done | 2001-05-21 | 2001-05-24 | 4/19 Vincent mail
6.11 | Complete reconciliation procedure. | Reconciliation procedure |  | Francis/Associates | Done | 2001-05-21 | 2001-05-24 | 4/19 Vincent mail
6.12 | Complete reconciliation procedure. | Reconciliation procedure |  | Auth | Done | 2001-05-21 | 2001-05-16 | 4/19 Vincent mail
6.13 | Complete reconciliation procedure. | Reconciliation procedure |  | Citiphone | Done | 2001-05-21 | 2001-05-24 | 4/19 Vincent mail
6.14 | Complete reconciliation procedure. | Reconciliation procedure |  | Erica/RM | Done | 2001-05-21 | 2001-05-24 | 4/19 Vincent mail
6.15 | Complete reconciliation procedure. | Reconciliation procedure |  | Marketing | Done | 2001-05-11 | 2001-05-17 | 4/19 Vincent mail
6.16 | Complete reconciliation procedure. | Reconciliation procedure |  | Tech | Done | 2001-05-21 | 2001-05-24 | 4/19 Vincent mail
6.17 | Communicate to all involved parties about the PIN mailer processing for Associates converted a/c's | Notification |  | TSG/Aftab | Cancelled (4/27 O&T meeting) | 2001-04-27 | 2001-05-24 | 4/25 tele-con
6.18 | All reconciliation procedures reviewed and certified by QA | QA confirmation |  | Tech | Done | 2001-05-21 | 2001-06-07 | 4/27 tele-con
6.19 | Provide a trial tape for RCC for a test read. | Trail Tape delivered to Tech |  | Francis/Associates | Done | 2001-05-07 |  | 4/27 tele-con
6.20 | Arrange dedicated LU and test transmission | LU # |  | Tech | Done | 2001-05-03 | 2001-05-02
6.21 | Test file upload (Volume 38~40MB) | Test Result |  | Tech | Done | 2001-05-04 | 2001-05-07
6.22 | Handling/checking procedure for customers having address changed after 4/25 |  |  | Auth | Done | 2001-05-11 | 2001-07-13 | 5/4 tel-con
6.23 | Set up a conference phone for the team to have daily status update since 6/10. |  |  | Amy | Done | 2001-05-08 |  | 5/4 tel-con
6.24 | Provide a test plan for the Live Test Cards |  |  | Vincent/Gordon | Done | 2001-05-11 | 2001-06-08 | 5/4 tel-con
6.25 | Develop a solution/procedure for removing the "I" type address within 1 month after conversion. |  |  | Tech | Cancelled | 2001-05-25 |  | 5/18 tel-con
6.26 | Provide # of a/c and CIF as of 4/25 |  |  | Telly/Associates | Done | 2001-05-18 | 2001-06-05 | 5/18 tel-con
6.27 | Provide # of a/c and CIF a week before 6/8 |  |  | Telly/Associates | Cancelled | 2001-06-01 |  | 5/18 tel-con
6.28 | Provide profile analysis of the declined customers |  |  | Telly/Associates | Done | 2001-05-18 | 2001-05-22 | 5/18 tel-con
6.29 | Provide a statistic of customers having address line 3 |  |  | Telly/Associates | Done | 2001-05-18 | 2001-05-22 | 5/18 tel-con
6.30 | Develop tool/utility to enable file exchange, as Citi new card number will not be available in the cross ref. File. |  |  | Tech | Done | 2001-05-18 | 2001-05-18 | 5/18 tel-con
6.31 | Finalize card mail-out date for the original 7/8 batch | 7/8. |  | Tech/TSG | Done | 2001-05-21 | 2001-05-25 | 5/18 tel-con
6.32 | Obtain concurrence of stakeholders (Christine, Esther and Aftab) on the service scope after September 30. |  |  | Citiphone | Pending by task owner | 2001-05-25 |  | 5/18 tel-con
6.33 | Charge back service take-over from BOOC | Figure out whether EDS system effort needed?? |  | TSG/Fraud | Pending by task owner | 2001-05-25 |  | 5/18 tel-con
7.0 | System User Requirements
7.1 | Set up encryption at both end |  | CGTI, Technology, and Citiphone | Eton Shu / Vincent Ku / Charlie Chao | Cancelled | N/A | N/A
7.2 | Fire wall (Associates + Citi) |  | CGTI, Technology, and Citiphone | Eton Shu / Vincent Ku / Charlie Chao | Cancelled | N/A | N/A
7.3 | Leverage equipment (server + PC) |  | CGTI, Technology, and Citiphone | Eton Shu / Vincent Ku / Charlie Chao | Cancelled | N/A | N/A
7.4 | Determine statement display -- Associates show 2 credit txn with Zero balance? Message for payment instruction? Show cash rebate of the month? | BOOC Stmt: 1 credit txn off setting total balcon'd Message instructing payment to Citi Cash rebate display as BAU |  | Mkting | Done | 2001-04-12 | 2001-04-12 | 4/12 meeting
7.5 | Determine customer mailing address and demographic conversion algorithm - for new and dual a/c |  |  | Citiphone | Done | 2001-04-12 | 2001-04-18 | 4/17,18 meeting
7.6 | Local system enhancement to adapt new txn codes |  |  | Tech | Done | 2001-05-11 | 2001-06-04
7.7 | Define new txn codes for transferred retail and fees |  |  | Marketing/TSG | Done | 2001-03-02
7.8 | Clarify Ed's requirement retarding NAS related data, e.g. demo and score, for subseq. process |  |  | Jeng | Cancelled | N/A | N/A
7.9 | Associates provide list of external interfaces | List provided to Vincent Ku |  | BOOC | Done | 2001-04-16 | 2001-04-16
7.10 | Collect requirement related to external interfaces | No need. | 7.9 | Tech | Done | 2001-04-16 | 2001-04-16
7.11 | Raise user requirement- Mkting |  |  | Mkting | Done | 2001-03-09 | 2001-03-09
7.12 | Raise user requirement- Risk Mgmt |  |  | RM | Done | 2001-03-09 | 2001-03-09
7.13 | Raise user requirement- RMS |  |  | Credit Op, | Done | 2001-03-09 | 2001-03-09
7.14 | Raise user requirement - Accounting |  |  | Accouting | Done | 2001-03-09 | 2001-03-09
7.15 | Raise user requirement - TCU |  |  | TCU | Done | 2001-03-09 | 2001-03-09
7.16 | Raise user requirement - Citiphone |  |  | Citiphone | Done | 2001-03-09 | 2001-03-09
7.17 | Raise user requirement- TSG |  |  | TSG | Done | 2001-03-09 | 2001-03-09
7.18 | Consolidate & sign-off user requirement |  |  | Tech | Done | 2001-03-09 | 2001-03-09
7.19 | Submit user requirement to RCC |  |  | Tech | Done | 2001-03-09 | 2001-03-09
7.20 | Raise SMR for ECS,OLA,CACS & RMS |  |  | Tech | Done | 2001-03-15 | 2001-03-15
7.21 | Raise SCR for Leigh Mardon card production for new card type. | SCR raised to CAP |  | TSG/Tech | Done | 2001-04-23 | 2001-04-24
7.22 | Raise SCR for . Card holder statement modification for new card type. | SCR raised to Jim Huang/Tech |  | TSG/Tech | Done | 2001-04-23 | 2001-04-24
7.23 | Raise data extraction (for mailing list) requirement in detail to Telly/Associates | Requirement |  | Mkting | Done | 2001-04-17 | 2001-04-17 | 4/17,18 meeting | 1.3
7.24 | Consult J/S for requirement regarding the reconciliation for letter printing/mailing. Raise requirement to Telly | Requirement |  | Sally/TSG | Done (BAU) | 2001-04-20 | 2001-04-19 | 4/17,18 meeting | 1.4
7.25 | Determing file layout requirement for "selected card list(to be kept for future reference)." Raise requriement to Telly. | Requirement |  | Tech | Done | 2001-04-23 | 2001-04-19 | 4/17,18 meeting | 1.5
7.26 | Confirm CTI data file layout (e.g. # of supp, the valid value of the "group" field) | Requirement |  | Citiphone | Done | 2001-04-20 | 2001-04-20 | 4/17,18 meeting | 1.7
7.27 | Confirm source code file upload layout | File layout |  | RM | Done | 2001-05-06 | 2001-05-28 | 4/17,18 meeting | 4.5
7.28 | Confirm BOOC statement message design for balcon'd account | Statement Message design by BOOC |  | Francis/Associates | Done | 2001-04-20 | 2001-04-19 | 4/17,18 meeting | 5.1
7.29 | Confirm insertion (to card carrier) design for converted account | ` |  | Mkting | Done | 2001-05-30 | 2001-05-22 | 4/17,18 meeting | 6.8
8.0 | System Development
8.1 | Finalize functional spec. |  |  | RCC | Done | 2001-04-12 | 2001-04-12
8.2 | Sign-off functional spec. |  |  | RCC/Tech | Done | 2001-04-16 | 2001-04-18
8.3 | Sign-off EDS function spec. |  |  | RCC/Tech/Francis | Done | 2001-04-27 | 2001-06-06
8.4 | Software development - ECS |  |  | RCC | Done | 2001-05-06 | 2001-05-06
8.5 | Software development - EDS |  |  | Associates | Done | 2001-05-06 | 2001-05-06
8.6 | Software development - Local |  |  | Tech | done | 2001-05-06 | 2001-06-04
8.7 | Apply for parameter setting (new cardtypes for UAT and Production) |  |  | RM | Cancelled (see 9.1) | 2001-04-23 | 2001-04-23
9.0 | UAT
9.1 | New Cardtype Parameter Setting (for UAT and Production) |  |  | Wen Shirley Hsu | Done | 2001-04-23 | 2001-04-23
9.2 | Coordinate SE to set up dummy merchant no. for balcon retail upload. | Dummy mcht no provided to TSG |  | Jack/Tech | Done | 2001-04-20 | 2001-04-19 | 4/17-18 meeting | 5.1
9.3 | Add new txn desc to systems wherever necessary |  |  | Sally/TSG | Done | 2001-04-20 | 2001-04-19 | 2001-04-12
9.4 | UAT kick-off meeting |  |  | Jack/Tech | Done | 2001-04-23 | 2001-04-23
9.5 | Quality check on UAT plan |  |  | Jack/Vincent/RCC | Done | 2001-04-30 | 2001-04-30 | 4/20 tele-con
9.6 | UAT resource allocation |  |  | Jack/Tech | Done | 2001-04-23 | 2001-04-23
9.7 | Complete UAT Plans |  |  | Jack/Tech | Done | 2001-04-27 | 2001-04-27
9.8 | Complete testing cases |  |  | Jack/Tech | Done | 2001-04-27 | 2001-04-27
9.9 | Set up UAT environment |  |  | Jack/Tech | Done | 2001-05-06 | 2001-05-06
9.10 | UAT |  |  | Jack/Tech | Done | 2001-05-18 | 2001-06-04
9.11 | Sign-off UAT |  |  | Jack/Tech | Done | 2001-05-20 | 2001-06-04
10.0 | Conversion & Balcon; Reconciliation
10.1 | Backup of Associates JOCS database |  |  | EDS | Done | 4/25 | 2001-04-25 | 4/17-18 meeting | 1.1
10.2 | Extraction of full Associates card base |  |  | EDS | Done | 4/25 | 2001-04-25 | 4/17-19 meeting | 1.2
10.3 | Generate mail out account list |  |  | Telly/Associates | Done | 2001-04-26 | 2001-04-26 | 4/17-20 meeting | 1.3
10.4 | Generate mail out account list SAS program |  |  | Telly/Associates | Done | 2001-05-03 | 2001-05-03 | 5/2 Vincent mail | 1.31
10.5 | Notice letters formatting and mail out |  |  | Jardine Salmat | Done | 2001-05-04 | 2001-05-04 | 4/17-21 meeting | 1.4
10.6 | Generate selected card list |  |  | EDS | Done | 2001-04-26 | 2001-04-26 | 4/17-22 meeting | 1.5
10.7 | Update the selected card list back to JOCS |  |  | EDS | Done | 2001-04-26 | 2001-05-02 | 4/17-23 meeting | 1.6
10.8 | Generate Citiphone/Citibank CTI data |  |  | Telly/Associates | Cancelled | 2001-05-02 | 2001-05-02 | 4/17-24 meeting | 1.7
10.9 | Load CTI data | Legal issue: customer privacy act. |  | Citiphone | Cancelled | 2001-05-02 | 2001-05-10 | 4/27 O&T meeting | 1.8
10.10 | Provide # of "dispute a/c as of the database cut-off date. | # of dispute a/c = 343 provided to RM |  | BOOC | Done | 2001-04-27 | 2001-04-26
10.11 | Provide # of "dispute a/c occurred between database cut-off ~ conversion cut-off. | # of dispute a/c |  | BOOC | Done | 2001-06-09 | 2001-06-08
10.12 | Negative consent update |  |  | EDS | Done | 5/4/2001 ~ 6/8/2001 | 2001-06-08 | 4/17-26 meeting | 2.1
10.13 | EDS close accounts responded negative |  |  | EDS | Done | 2001-06-08 | 2001-06-07 | 4/17-27 meeting | 2.11
10.14 | Backup JOCS database |  |  | EDS | Done | 2001-06-08 | 2001-06-07 |  | 2.12
10.15 | Generate converted account report |  |  | EDS | Done | 2001-06-09 | 2001-06-08 | 4/17-28 meeting | 2.2
10.16 | Generate conversion upload files |  |  | EDS | Done | 2001-06-09 | 2001-06-08 | 4/17-29 meeting | 2.4
10.17 | Conversion upload files ASCII-EBCDIC conversion |  |  | Technology/Citibank | Done | 2001-06-09 | 2001-06-08 | 4/17-30 meeting | 2.6
10.18 | Conversion upload files uploaded by cycle |  |  | Technology/Citibank | Done | 2001-06-09 | 6/11, 6/19, 6/21 | 4/17-31 meeting | 3.1
10.19 | Conversion account validation in ECS (including exception) |  |  | Citiphone | Done | 2001-07-01 | 6/12~7/1 | 4/17-33 meeting | 3.3
10.20 | Conversion address mismatch exception report handling |  |  | Citiphone | Cancelled | 2001-06-10 | N/A | 4/17-34 meeting | 3.4
10.21 | Conversion exception report handling |  |  | Tech/User | Cancelled | 2001-06-10 | N/A | 4/17-35 meeting | 3.5
10.22 | Citibank/Associates cross reference file |  |  | RCC | Done | 7/3/2001 | 6/12~7/1 | 4/17-36 meeting | 3.6
10.23 | Cross reference update to EDS |  |  | EDS | Done | 7/3/2001 | 6/12~7/1 | 4/17-37 meeting | 3.7
10.24 | Card embossing |  |  | Leigh Mardon/TSG | Done | 7/3/2001 | 6/12~7/1 | 4/17-38 meeting | 3.8
10.25 | Conversion accounts overall reconciliation & handling |  |  | Tech | Done | 7/3/2001 | 6/12~7/1 | 4/17-39 meeting | 3.9
10.26 | Generate authorization file using Balcon file format to ECS (D1-8) |  |  | EDS | Done | 6/30/2001, 7/9/2001, 7/18/2001, 6/21/2001 | 6/30/2001, 7/9/2001, 7/18/2001, 6/21/2001 | 4/17-40 meeting | 3.10
10.27 | Authorization file upload in Balcon retail format |  |  | Tech | Done | 7/1/2001, 7/10/2001, 7/19/2001, 6/22/2001 | 7/1/2001, 7/10/2001, 7/19/2001, 6/22/2001 | 4/17-41 meeting | 3.11
10.28 | Authorization file upload verification |  |  | Auth./Citibank | Done | 7/2/2001, 7/11/2001, 7/20/2001, 6/23/2001 | 7/2/2001, 7/11/2001, 7/20/2001, 6/23/2001 | 4/17-42 meeting | 3.12
10.29 | Embossing cards mail out (D1-8) |  |  | Leigh Mardon/TSG | Done | 6/29/2001, 7/6/2001, 7/17/2001, 6/20/2001 | 6/29/2001, 7/6/2001, 7/17/2001, 6/20/2001 | 4/17-43 meeting | 3.13
10.30 | Release pre-auth total used line |  |  | RCC | Done | 7/8/2001, 7/17/2001, 7/26/2001, 6/29/2001 | 7/8/2001, 7/17/2001, 7/26/2001, 6/29/2001 | 4/17-44 meeting | 3.14
10.31 | Acitivation file for Associates to block cards |  |  | RCC | Done | 6/23/2001 ~ 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | 6/23/2001 ~ 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | 4/17-45 meeting | 3.15
10.32 | Activation firle for Associates to block cards. |  |  | Tech | Cancelled | 6/20/2001 ~ 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | N/A | 9/4 mail | 3.151
10.33 | Block the Associates card for those Citibank credit card activated |  |  | EDS | Done | 6/24/2001 ~ 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | 6/24/2001 ~ 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | 4/17-46 meeting | 3.16
10.34 | Late write-in decline - card & card carrier pick-up |  |  | Leigh Mardon/TSG | Done | 6/8/2001 ~ 7/25/2001 | 6/8/2001 ~ 7/25/2001 | 4/27 tele-con | 3.17
10.35 | Late write-in decline - ECS account cancellation |  |  | CIM | Done | 6/8/2001 ~ 7/25/2001 | 6/8/2001 ~ 7/25/2001 |  | 3.171
10.36 | Refund annual fee by ratio for Platinum for cycle 16th, 25th and 28th |  |  | Associates | Done | 2001-06-01 | 2001-06-01 | 4/17-47 meeting | 4.1
10.37 | Refund annual fee by ratio for Platinum for cycle 7th. |  |  | Associates | Done | 2001-07-01 | 2001-07-01 | 4/17-48 meeting | 4.2
10.38 | Refund double cash rebate fee, if any, for cycle 16th, 25th and 28th. |  |  | Associates | Done | 6/1 | 6/1 | 4/17-49 meeting | 4.3
10.39 | Refund double cash rebate fee, if any, for cycle 7th. |  |  | Associates | Done | 2001-07-01 | 2001-07-01 | 4/17-50 meeting | 4.4
10.40 | Risk Management update source code back to ECS |  |  | Erica/RM | Done | 2001-06-15 | 2001-09-12 | 4/17-51 meeting | 4.5
10.41 | Cardmember bill a/c checking |  |  | TCU | Done | 7/7,8/2001, 7/16,17/2001, 7/25,26/2001, 6/28, 29/2001 | 7/7,8/2001, 7/16,17/2001, 7/25,26/2001, 6/28, 29/2001 |  | 4.6
10.42 | Backup of Associates JOCS database |  |  | EDS | Done | 7/7/2001, 7/16/2001, 7/25/2001, 6/28/2001 | 7/7/2001, 7/16/2001, 7/25/2001, 6/28/2001 |  | 5.01
10.43 | EDS generates the retail Balcon |  |  | EDS | Done | 7/7/2001, 7/16/2001, 7/25/2001, 6/28/2001 | 7/7/2001, 7/16/2001, 7/25/2001, 6/28/2001 | 4/17-52 meeting | 5.1
10.44 | EDS generates the interest/fee/credit Balcon |  |  | EDS | Done | 7/7/2001, 7/16/2001, 7/25/2001, 6/28/2001 | 7/7/2001, 7/16/2001, 7/25/2001, 6/28/2001 | 4/17-53 meeting | 5.2
10.45 | Balcon retail upload file layout validation and ASCII-EBCDIC conversion |  |  | Technology/Citibank | Done | 7/8/2001, 7/17/2001, 7/26/2001, 6/29/2001 | 7/8/2001, 7/17/2001, 7/26/2001, 6/29/2001 | 4/17-54 meeting | 5.3
10.46 | Balcon Nixdorf upload file layout validation and ASCII-EBCDIC conversion |  |  | Technology/Citibank | Done | 7/8/2001, 7/17/2001, 7/26/2001, 6/29/2001 | 7/8/2001, 7/17/2001, 7/26/2001, 6/29/2001 | 4/17-55 meeting | 5.4
10.47 | Balcon retail and Nixdorf upload to ECS |  |  | Technology/Citibank | Done | 7/8/2001, 7/17/2001, 7/26/2001, 6/29/2001 | 7/8/2001, 7/17/2001, 7/26/2001, 6/29/2001 | 4/17-56 meeting | 5.5
10.48 | Balcon results verification - a/c detail |  |  | Citiphone | Done | 7/9/2001, 7/18/2001, 7/27/2001, 6/30/2001 | 7/9/2001, 7/18/2001, 7/27/2001, 6/30/2001 | 4/17-57 meeting | 5.6
10.49 | Balcon results verification - Fund transfer result verification |  |  | TP/TSG | Done | 7/9/2001, 7/18/2001, 7/27/2001, 6/30/2001 | 7/9/2001, 7/18/2001, 7/27/2001, 6/30/2001 | 4/17-58 meeting | 5.61
10.50 | Cardmember bill a/c checking |  |  | TCU | Done | 7/9/2001, 7/18/2001, 7/27/2001, 6/30/2001 | 7/9/2001, 7/18/2001, 7/27/2001, 6/30/2001 |  | 5.62
10.51 | EDS reduce the Associates account credit line by the Balcon amount for conversion accounts. |  |  | EDS | Done | 7/7/2001, 7/16/2001, 7/25/2001, 6/28/2001 | 7/7/2001, 7/16/2001, 7/25/2001, 6/28/2001 | 4/17-59 meeting | 5.7
10.52 | Zero out the statement balance for those conversion accounts; Statement printing and mail out. |  |  | EDS/Associate statement vendor | Done | 7/8/2001, 7/17/2001, 7/26/2001, 6/29/2001 | 7/8/2001, 7/17/2001, 7/26/2001, 6/29/2001 | 4/17-60 meeting | 5.8
10.53 | Citibank statement printing and mail out. |  |  | Judine Salmat/TSG | Done | 7/10/2001, 7/19/2001, 7/28/2001, 7/2/2001 | 7/10/2001, 7/19/2001, 7/28/2001, 7/2/2001 | 4/17-61 meeting | 5.9
10.54 | Generate the line used authorization file for those Associates accounts that Citibank credit card non-activated for cycle 7th. |  |  | EDS | Done | 7/10/2001, 7/17/2001, 7/24/2001, 7/31/2001 | 7/10/2001, 7/17/2001, 7/24/2001, 7/31/2001 | 4/17-62 meeting | 5.10
10.55 | Associates cycle 7th accounts with Citibank credit card non-activated authorization file validation and upload |  |  | Technology/Citibank | Done | 7/11/2001, 7/18/2001, 7/25/2001, 8/1/2001 | 7/11/2001, 7/18/2001, 7/25/2001, 8/1/2001 | 4/17-63 meeting | 5.11
10.56 | Associates cycle 7th accounts with Citibank credit card non-activated authorization file upload verification |  |  | Auth./Citibank | Done | 7/12/2001, 7/19/2001, 7/26/2001, 8/2/2001 | 7/12/2001, 7/19/2001, 7/26/2001, 8/2/2001 | 4/17-64 meeting | 5.12
10.57 | Associates cycle 7th accounts with Citibank credit card non-activated pre-auth total used line release verification. |  |  | Auth./Citibank | Done | 8/9/2001, 7/19/2001, 7/26/2001, 8/2/2001 | 8/9/2001, 7/19/2001, 7/26/2001, 8/2/2001 | 4/17-65 meeting | 5.13
10.58 | Generate the line used authorization file for those Associates accounts that Citibank credit card non-activated for cycle 16th. |  |  | EDS | Done | 7/19/2001, 7/26/2001, 8/2/2001, 8/9/2001 | 7/19/2001, 7/26/2001, 8/2/2001, 8/9/2001 | 4/17-66 meeting | 5.14
10.59 | Associates cycle 16th accounts with Citibank credit card non-activated authorization file validation and upload |  |  | Technology/Citibank | Done | 7/20/2001, 7/27/2001, 8/3/2001, 8/10/2001 | 7/20/2001, 7/27/2001, 8/3/2001, 8/10/2001 | 4/17-67 meeting | 5.15
10.60 | Associates cycle 16th accounts with Citibank credit card non-activated authorization file upload verification |  |  | Auth./Citibank | Done | 7/21/2001, 7/28/2001, 8/4/2001, 8/11/2001 | 7/21/2001, 7/28/2001, 8/4/2001, 8/11/2001 | 4/17-68 meeting | 5.16
10.61 | Associates cycle 16th accounts with Citibank credit card non-activated pre-auth total used line release verification. |  |  | Auth./Citibank | Done | 8/18/2001, 7/28/2001, 8/4/2001, 8/11/2001 | 8/18/2001, 7/28/2001, 8/4/2001, 8/11/2001 | 4/17-69 meeting | 5.17
10.62 | Generate the line used authorization file for those Associates accounts that Citibank credit card non-activated for cycle 25th. |  |  | EDS | Done | 7/28/2001, 8/4/2001, 8/11/2001, 8/18/2001 | 7/28/2001, 8/4/2001, 8/11/2001, 8/18/2001 | 4/17-70 meeting | 5.18
10.63 | Associates cycle 25th accounts with Citibank credit card non-activated authorization file validation and upload |  |  | Technology/Citibank | Done | 7/29/2001, 8/5/2001, 8/12/2001, 8/19/2001 | 7/29/2001, 8/5/2001, 8/12/2001, 8/19/2001 | 4/17-71 meeting | 5.19
10.64 | Associates cycle 25th accounts with Citibank credit card non-activated authorization file upload verification |  |  | Auth./Citibank | Done | 7/30/2001, 8/6/2001, 8/13/2001, 8/20/2001 | 7/30/2001, 8/6/2001, 8/13/2001, 8/20/2001 | 4/17-72 meeting | 5.20
10.65 | Associates cycle 25th accounts with Citibank credit card non-activated pre-auth total used line release verification. |  |  | Auth./Citibank | Done | 8/27/2001, 8/6/2001, 8/13/2001, 8/20/2001 | 8/27/2001, 8/6/2001, 8/13/2001, 8/20/2001 | 4/17-73 meeting | 5.21
10.66 | Generate the line used authorization file for those Associates accounts that Citibank credit card non-activated for cycle 28th. |  |  | EDS | Done | 6/30/2001, 7/7/2001, 7/14/2001, 7/21/2001 | 6/30/2001, 7/7/2001, 7/14/2001, 7/21/2001 | 4/17-74 meeting | 5.22
10.67 | Associates cycle 28th accounts with Citibank credit card non-activated authorization file validation and upload |  |  | Technology/Citibank | Done | 7/1/2001, 7/8/2001, 7/15/2001, 7/22/2001 | 7/1/2001, 7/8/2001, 7/15/2001, 7/22/2001 | 4/17-75 meeting | 5.23
10.68 | Associates cycle 28th accounts with Citibank credit card non-activated authorization file upload verification |  |  | Auth./Citibank | Done | 7/2/2001, 7/9/2001, 7/16/2001, 7/23/2001 | 7/2/2001, 7/9/2001, 7/16/2001, 7/23/2001 | 4/17-76 meeting | 5.24
10.69 | Associates cycle 28th accounts with Citibank credit card non-activated pre-auth total used line release verification. |  |  | Auth./Citibank | Done | 7/30/2001, 7/9/2001, 7/16/2001, 7/23/2001 | 7/30/2001, 7/9/2001, 7/16/2001, 7/23/2001 | 4/17-77 meeting | 5.25
10.70 | Backup of Associates JOCS database |  |  | EDS | Done | 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 |  | 6.01
10.71 | EDS generates the pipeline retail Balcon |  |  | EDS | Done | 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | 4/17-78 meeting | 6.1
10.72 | EDS generates the pipeline interest/fee/credit Balcon |  |  | EDS | Done | 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | 4/17-79 meeting | 6.2
10.73 | Balcon pipeline retail upload file layout validation and ASCII-EBCDIC conversion |  |  | Technology/Citibank | Done | 8/8/2001, 8/17/2001, 8/26/2001, 7/29/2001 | 8/8/2001, 8/17/2001, 8/26/2001, 7/29/2001 | 4/17-80 meeting | 6.3
10.74 | Balcon pipeline Nixdorf upload file layout validation and ASCII-EBCDIC conversion |  |  | Technology/Citibank | Done | 8/8/2001, 8/17/2001, 8/26/2001, 7/29/2001 | 8/8/2001, 8/17/2001, 8/26/2001, 7/29/2001 | 4/17-81 meeting | 6.4
10.75 | Balcon retail and Nixdorf Files Transfer to ECS |  |  | Technology/Citibank | Done | 8/8/2001, 8/17/2001, 8/26/2001, 7/29/2001 | 8/8/2001, 8/17/2001, 8/26/2001, 7/29/2001 |  | 6.41
10.76 | Balcon pipeline results verification - a/c details |  |  | Citiphone | Done | 8/9/2001, 8/18/2001, 8/27/2001, 7/30/2001 | 8/9/2001, 8/18/2001, 8/27/2001, 7/30/2001 | 4/17-82 meeting | 6.5
10.77 | Balcon results verification - Fund transfer result verification |  |  | TP/TSG | Done | 8/9/2001, 8/18/2001, 8/27/2001, 7/30/2001 | 8/9/2001, 8/18/2001, 8/27/2001, 7/30/2001 | 4/17-83 meeting | 6.51
10.78 | Cardmember bill a/c checking |  |  | TCU | Done | 8/9/2001, 8/18/2001, 8/27/2001, 7/30/2001 | 8/9/2001, 8/18/2001, 8/27/2001, 7/30/2001 |  | 6.52
10.79 | EDS close those accounts that Citibank credit card still non-activated. |  |  | EDS | Done | 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | 8/7/2001, 8/16/2001, 8/25/2001, 7/28/2001 | 4/17-84 meeting | 6.6
10.80 | Zero out the statement balance for those accounts that Citibank credit card non-activated. Statement printing and mail out. |  |  | EDS/Associate statement vendor | Done | 8/8/2001, 8/17/2001, 8/26/2001, 7/29/2001 | 8/8/2001, 8/17/2001, 8/26/2001, 7/29/2001 | 4/17-85 meeting | 6.7
10.81 | Citibank statement printing and mail out. |  |  | Judine Salmat/TSG | Cancelled | 8/10/2001, 8/19/2001, 8/28/2001, 8/2/2001 |  | 4/17-86 meeting | 6.8
10.82 | Backup of Associates JOCS database |  |  | EDS | In progress | 9/7/2001, 9/16/2001, 9/25/2001, 8/28/2001 |  |  | 7.01
10.83 | EDS generates the pipeline retail Balcon |  |  | EDS | In progress | 9/7/2001, 9/16/2001, 9/25/2001, 8/28/2001 |  | 4/17-87 meeting | 7.1
10.84 | EDS generates the pipeline interest/fee/credit Balcon |  |  | EDS | In progress | 9/7/2001, 9/16/2001, 9/25/2001, 8/28/2001 |  | 4/17-88 meeting | 7.2
10.85 | Balcon pipeline retail upload file layout validation and ASCII-EBCDIC conversion |  |  | Technology/Citibank | In progress | 9/8/2001, 9/17/2001, 9/26/2001, 8/29/2001 |  | 4/17-89 meeting | 7.3
10.86 | Balcon pipeline Nixdorf upload file layout validation and ASCII-EBCDIC conversion |  |  | Technology/Citibank | In progress | 9/8/2001, 9/17/2001, 9/26/2001, 8/29/2001 |  | 4/17-90 meeting | 7.4
10.87 | Balcon retail and Nixdorf Files Transfer to ECS |  |  | Technology/Citibank | In progress | 9/8/2001, 9/17/2001, 9/26/2001, 8/29/2001 |  |  | 7.41
10.88 | Balcon pipeline results verification- a/c detail |  |  | Citiphone | In progress | 9/9/2001, 9/18/2001, 9/27/2001, 8/30/2001 |  | 4/17-91 meeting | 7.5
10.89 | Balcon results verification - Fund transfer result verification |  |  | TP/TSG | In progress | 9/9/2001, 9/18/2001, 9/27/2001, 8/30/2002 |  | 4/17-92 meeting | 7.51
10.90 | Cardmember bill a/c checking |  |  | TCU | In progress | 9/9/2001, 9/18/2001, 9/27/2001, 8/30/2002 |  |  | 7.52
10.91 | Zero out the statement balance for those accounts that Citibank credit card non-activated. Statement printing and mail out. |  |  | EDS/Associate statement vendor | In progress | 9/8/2001, 9/17/2001, 9/26/2001, 8/29/2001 |  | 4/17-93 meeting | 7.6
10.92 | Citibank statement printing and mail out. |  |  | Judine Salmat/TSG | Cancelled | 9/10/2001, 9/19/2001, 9/28/2001, 9/2/2001 |  | 4/17-94 meeting | 7.7
10.93 | Cardholder application forms original verification |  |  | CIM | Done | 7/1/2001 ~ 8/31/2001 | 7/1/2001 ~ 8/31/2001 |  | 8.1
10.94 | Generate Citi card Numbers for Cardif policy holders |  |  | Tech/Citi | Done | 2001-07-05 | 1918-05-01 |  | 8.2
10.95 | Repayment to BOOC after Balcon - Normal |  |  | TPD | In progress | 6/30/2001 ~ 9/25/2001 |  |  | 8.3
10.96 | Repayment to BOOC after Balcon - Dispute |  |  | PRD | In progress | 6/30/2001 ~ 9/25/2001 |  |  | 8.4
10.97 | Set up Special Handling Procedure | Procedure |  | Tech/CPO/TSG/Fraud | Done | 2001-06-27 | 2001-06-27
10.98 | Report to mgmt the number of returned card mails | Daily Progress Report |  | Tech | Done | 2001-06-23 | 2001-06-28
10.99 | Generate Citi card numbers for BOOC Cardif policy holders |  |  | Tech | Done | 2001-07-05 | 2001-07-05

## MyATM專案時程
Task No. | Planned |  |  | Main-Task | Sub-Task | Owners | Status | Remarks
| Sprint | Start date | End date
1. 功能梳理與畫面設計 | [6 empty] | 0%
1.1.1 |  | 2019-07-01 | 2019-07-05 |  | MyATM流程梳理
1.1.2 |  | 2019-07-08 | 2019-07-19 |  | PM流程頁面規劃
1.1.3 |  | 2019-07-22 | 2019-07-22 |  | PM提供頁面內容
1.1.4 |  | 2019-07-23 | 2019-08-09 |  | ART設計畫面/討論
1.1.5 |  | 2019-08-12 | 2019-08-16 |  | 切版
2. 系統架構設計與開發 | [6 empty] | 0%
2.1.1 | sprint 1 | 2019-07-08 | 2019-07-19 |  | 整體架構規劃參照柬埔寨AP |  | 0%
2.1.2 | sprint 1 | 2019-07-08 | 2019-07-19 |  | 電文發送模組 |  | 0%
2.1.3 | sprint 1 | 2019-07-08 | 2019-07-19 |  | DB操作模組 |  | 0%
2.1.4 | sprint 1 | 2019-07-08 | 2019-07-19 |  | 新舊DB資料整合轉移 |  | 0%
2.1.5 | sprint 2 | 2019-07-22 | 2019-08-02 |  | 電文發送模組 |  | 0%
2.1.6 | sprint 2 | 2019-07-22 | 2019-08-02 |  | 商業邏輯層建置 |  | 0%
2.1.7 | sprint 2 | 2019-07-22 | 2019-08-02 |  | WEB server共用 Layout |  | 0%
2.1.8 | sprint 3 | 2019-08-05 | 2019-08-16 |  | 讀卡機元件操作模組 |  | 0%
2.1.9 | sprint 3 | 2019-08-05 | 2019-08-16 |  | 批次清查改寫 |  | 0%
3. 系統開發/測試 | [6 empty] | 0%
首頁與登入 | [6 empty] | 0%
3.1.1 | sprint 4 | 2019-08-19 | 2019-08-30 |  | 登入畫面 |  | 0% | 需Art提供畫面
3.1.2 | sprint 4 | 2019-08-19 | 2019-08-30 |  | 說明畫面 |  | 0% | 需Art提供畫面
3.1.3 | sprint 4 | 2019-08-19 | 2019-08-30 |  | 登入-AP商業邏輯 |  | 0%
3.1.4 | sprint 5 | 2019-09-02 | 2019-09-13 |  | 登入畫面 |  | 0%
3.1.5 | sprint 5 | 2019-09-02 | 2019-09-13 |  | 選單畫面 |  | 0%
3.1.6 | sprint 5 | 2019-09-02 | 2019-09-13 |  | 登入-AP商業邏輯 |  | 0%
轉帳服務 | [6 empty] | 0%
3.2.1 | sprint 6 | 2019-09-16 | 2019-09-27 |  | 我的常用帳號 |  | 0% | 需Art提供畫面
3.2.2 | sprint 6 | 2019-09-16 | 2019-09-27 |  | 我的常用帳號-AP商業邏輯 |  | 0%
3.2.3 | sprint 6 | 2019-09-16 | 2019-09-27 |  | 轉入約定帳號 |  | 0% | 需Art提供畫面
3.2.4 | sprint 6 | 2019-09-16 | 2019-09-27 |  | 轉入約定帳號-AP商業邏輯 |  | 0%
3.2.5 | sprint 6 | 2019-09-16 | 2019-09-27 |  | 轉入其它帳號 |  | 0% | 需Art提供畫面
3.2.6 | sprint 6 | 2019-09-16 | 2019-09-27 |  | 轉入其它帳號-AP商業邏輯 |  | 0%
餘額/明細 | [6 empty] | 0%
3.3.1 | sprint 7 | 2019-09-30 | 2019-10-11 |  | 餘額查詢畫面 |  | 0% | 需Art提供畫面
3.3.2 | sprint 7 | 2019-09-30 | 2019-10-11 |  | 餘額查詢-AP商業邏輯 |  | 0%
3.3.3 | sprint 7 | 2019-09-30 | 2019-10-11 |  | 帳戶交易明細畫面 |  | 0% | 需Art提供畫面
3.3.4 | sprint 7 | 2019-09-30 | 2019-10-11 |  | 帳戶交易明細-AP商業邏輯 |  | 0%
3.3.5 | sprint 8 | 2019-10-14 | 2019-10-25 |  | MyMemo轉出明細 |  | 0% | 需Art提供畫面
3.3.6 | sprint 8 | 2019-10-14 | 2019-10-25 |  | MyMemo轉出明細-AP商業邏輯 |  | 0%
申請/變更/設定 | [6 empty] | 0%
3.4.1 | sprint 8 | 2019-10-14 | 2019-10-25 |  | 常用帳戶設定畫面 |  | 0% | 需Art提供畫面
3.4.2 | sprint 8 | 2019-10-14 | 2019-10-25 |  | 常用帳戶設定-AP商業邏輯 |  | 0%
3.4.3 | sprint 9 | 2019-10-28 | 2019-11-08 |  | 個人資料設定畫面 |  | 0% | 需Art提供畫面
3.4.4 | sprint 9 | 2019-10-28 | 2019-11-08 |  | 個人資料設定-AP商業邏輯 |  | 0%
3.4.5 | sprint 9 | 2019-10-28 | 2019-11-08 |  | 網銀密碼畫面 |  | 0% | 需Art提供畫面
3.4.6 | sprint 9 | 2019-10-28 | 2019-11-08 |  | 網銀密碼-商業邏輯 |  | 0%
3.4.7 | sprint 10 | 2019-11-11 | 2019-11-22 |  | 變更晶片卡密碼 |  | 0% | 需Art提供畫面
4. SIT
4.1 | sprint 10 | 2019-11-11 | 2019-11-22 |  | SIT |  | 0%
5. UAT
5.1 |  | 2019-11-25 | 2019-12-06 |  | UAT | user
6. 上線準備
6.1 |  | 2019-11-25 | 2019-12-06 |  | DB資料移轉 | uat同時進行 | 1wks
6.2 |  | 2019-11-25 | 2019-12-06 |  | 批次申請設定
6.3 |  | 2019-11-25 | 2019-12-06 |  | .Net Core安裝
6.4 |  | 2019-11-25 | 2019-12-06 |  | 原始碼掃描

## Schedule (hidden)
Task | 工作天 | 開始日期 | 結束日期
功能梳理
公文簽呈 | 30 days
功能開發 | 60 days
SIT | 10 days
UAT
UAT測試報告
客戶引導
上線前準備
上線

## Operation Task Force List (hidden)
Associate Project Team Member Phone Contact List
Name | Phone Number | E-mail Address
Project Management
Betty Tsoi | 8725-5042 | Tsoi, Betty C.
Marketing
Christine Teng | 8725-5268 | Teng, Christine K.H.
Rick Chen | 8725-5265 | Chen, Rick N.Y.
Wen Chuang | 8725-5274 | Chuang, Wen W.H.
Risk Management
Jeng Lee | 8725-5389 | Lee, Jeng
Theresa Liao | 8725-5390 | Liao, Theresa
Erica Lu | 8725-5395 | Lu, Erica
Credit Operations
Esther Teng | 2522-7891 | Tang, Esther
Ward Wen | 2522-7722 | Wen, Ward H.Y.
Ron Goodman | 2522-7654 | Goodman, Ronald
Judy Chen | 2522-7455 | Chen, Judy M.
Alice Liu | 2522-7793 | Liu, Alice
O&T
Aftab Ahmed | 8725-5288 | Ahmed, Aftab
TSG
Vincent Chen | 2522-7779 | Chen, Vincent M.T.
Jerry Wang | 2522-7865 | Wang, Jerry N. C.
Sally Wang | 2522-6539 | Wang, Sally
Paulina Shen | 2522-7712 | Shen, Paulina
Citiphone
Daniel Huang |  | Huang, Dainel H.C.
Joy Tien | 2576-2960 | Tien, Joy N.L.
Ivy Yang | 2576-2446 | Yang, Ivy T.N.
TCU
Shirley Chen |  | Chen, Shirley H.C.
Annie Meng |  | Meng, Annie
Card Project Office/Tech
James Wu | 2522-7070 | Wu, James J.H.
Vincent Ku | 2522-7699 | Ku, Vincent C.H.
Jack Fu | 2522-7655 | Fu, Jack
Amy Lin | 2522-6050 | Lin, Amy L.C.
RCC
Gordon-K Chiu | 002-65-328-3137 | Chiu, Gordon-K
Barry Tan | 002-65-328-6017 | Tan, Barry H.P.
Soo-Chin Goh | 002-65-328-3161 | Goh, Soo-Chin
Associates
Roger Lo |  | rlo@afcc.com.tw
Frances Yeh | 2579-9193 | fryeh@afcc.com.tw
Telly Hou | 2579-9172 | thou@afcc.com.tw
FinCon
Kitty Fung | 8725-5318 | Fung, Kitty K.Y.
Legal/Comm
Sam Hong | 8725-5331 | Hong, Sam
Evelyn Lin | 8725-5333 | Lin, Evelyn Y.T.

## Management Stream Activites (hidden)
REF.# | ACTIVITY | DELIVERABLE | DEPENDENCIES | RESPONSIBLE | TARGET COMPLETION | STATUS
REGULATORY
IN-0010 | Obtain MOF approval to migrate Associates cardholders to Citibank without explicit customer concent | Approval to act on customers' response to invitation: (1) response +ve, (2) response -ve, (3) no response | IN-0040 | Sam / Lee & Li | 03/16/2001 03/30/2001 04/30/2001 | CLOSED - 4/25
IN-0015 | Obtain FTC approval to migrate Associates cardholders to Citibank without explicit customer concent | Approval to act on customers' response to invitation: (1) response +ve, (2) response -ve, (3) no response | IN-0040 | Sam / Lee & Li | 03/16/2001 03/27/2001 | CLOSED - 4/3
IN-0020 | - Send request to BOMA for waiver |  | IN-0040 |  | 03/06/2001 03/16/2001 | CLOSED - 4/3
IN-0030 | - Send request to FTC for waiver (Evelyn to confirm if necessary) |  | IN-0040 |  | 03/06/2001 03/13/2001 | CLOSED - 3/13
IN-0031 | Obtain Fed approval re: 23A/B | Update | None | Shariq | 2001-03-13 | CLOSED - 3/13, verbal update of approval
IN-0032 | Obtain written confirmation of Fed approval re: 23A/B | Confirmation in writing | IN-0031 | Shariq | 2001-03-23 | CLOSED - 3/21
IN-0033 | Prepare board resolution to change business operations of ACCTI and AFTI | Draft of resolutions | None | Sam | 2001-03-20 | CLOSED
IN-0034 | Obtain board approval | Approval of resolutions | IN-0033, IN-0037 | Rodney | 04/06/2001 04/16/2001 04/25/2001 05/03/2001 | 04/06 - resolution sent to board members. 04/18 - Rodney in meeting with board this week. 04/26 - pending corporate tax office approval. 05/04 CLOSED
IN-0035 | Prepare "purchase" contract to acquire ACCTI assets | Contract | None | Sam | 2001-04-27 | 4/24 - CLOSED. 04/26 - Re-opened
IN-0036 | Sign purchase contract | Signed contract | IN-035 | Shariq | 2001-06-15
IN-0037 | Obtain Corporate Tax Office approval | Approval | None | Shariq | 2001-04-28 | 05/01 - CLOSED
IN-0040 | Obtain verbal indication of approval via high-level dialog |  | None | Robert / Peter / Vita / Joyce | 2001-02-27 | CLOSED - 2/27/2001, verbal green light
MARKETING
IN-0050 | Propose features of Citibank BALCON program to Associates cardholders | Proposal of features in Chinese and English | None | Christine | 2001-02-16 | CLOSED
IN-0051 | Produce gap analysis of card features and ECS capability to facilitate re-packaging of offer if "forced" conversion is acceptable by MOF | Gap analysis - features, ECS capability to support | None | Christine | 2001-02-21 | WITHDRAWN, combined with IN-0052
IN-0052 | Finalize offers of BALCON | Offers for respective customer groups based on risk hierarchy, financial impact | IN-0130 | Christine | 2001-02-26 | CLOSED - 2/27/2001, 3-tiered reward points
IN-0053 | Finalize conversion strategies, flow and calendar | Conversion strategy, flow and calendar | IN-0040, IN-0134, IN-0136, IN-0139 | Christine | 2001-04-11 | CLOSED - 4/11
IN-0060 | Propose changes to existing Associates' terms & conditions for those customers who do not respond to BALCON program | Proposal of changes | IN-0040, Legal | Christine | 02/28/2001 03/26/2001 | 2/27 - consent assumed for no response, O/S - explicit decline. 4/16 - under legal review. 4/19 - Legal approval obtained
IN-0070 | Draft marketing letters to invite customers to BALCON | Draft letters | IN-0052, IN-0060, IN-0010 | Christine | 2001-03-16 | 2/27 - one mailing only after MOF/FTC/Fed approval, combined with IN-0080
IN-0075 | Produce marketing materials | Creatives | IN-0052,IN-0060 | Christine | 03/05/2001 03/30/2001 04/15/2001 | CLOSED - 4/16
IN-0080 | Draft communication letter to inform customers of conversion | Draft letter | IN-0040 | Christine / Joyce | 03/16/2001 03/30/2001 04/15/2001 | 2/27 - one mailing only after MOF approval. 4/16 - under legal review. 4/19 - Legal approval obtained.
WK-005 | Fine-tune marketing message wording | Marketting letter | None | Rick | 2001-04-17 | (WK-005, 006, 008, 009) 4/17 - under legal review. 4/19 - Legal approval obtained.
WK-007 | Translate marketing letter and statement messages, inserts into English | Marketing letter in English | WK-005 | Rick | 2001-04-18 | 4/24 - CLOSED
WK-010 | Emphasize "do not pay Associates, pay Citibank" message in last Associates statement before BALCON, and first Associates statement after BALCON, use statement insert | Statement message, insert | None | Rick / Roger | 2001-04-17 | (WK-010, 011) CLOSED - 5/15
WK-012 | Devise incentive to transfer those good customers who decline to BALCON | Scheme in place only, production of detailed logistics and materials will be determined by customer response | Customer response | Rick | 2001-04-20 | CLOSED - 05/23
WK-013 | Invite Associates customers whose accounts are being closed due to "blocked" status to BALCON, pending further credit analysis. | Invitation letter | WK-002 | Rick | 2001-04-17 | 4/17 - under review by Sam. 4/19 - Legal approval obtained.
IN-0085 | Send invitation letters to customer based on their risk hierarchy | Marketing letters | IN-0070, IN-0130, IN-0145 | Christine | 2001-03-16 | 2/27 - one mailing only after MOF/FTC/Fed approval, combined with IN-0086
IN-0086 | Send notification letter to inform customers of conversion | Notification letters | IN-0010, IN-0080, IN-0031, IN-0034 | Christine | 03/17/2001 04/02/2001 04/23/2001 05/04/2001 | 4/3 - Dependent on MOF approval. 05/04 - CLOSED
RISK MANAGEMENT
IN-0090 | Create loss reserve by requesting for restructuring reserve | Confirmation from Eduardo | IN-0100, NY response | Shariq | 03/31/2001 04/09/2001 | 4/3 - input sent to Eduardo for NY approval. 4/13 - clarification sought & reverted
IN-0100 | Estimate loss reserve | Loss estimation | None | Jeng | 2001-03-23
- due to credit (did not pass scoring, delinquent)
- due to potential fraud in inactivating/activating card
IN-0110 | Understand multiplier used by Associates in setting credit line | Credit line increase to boost activation rate | None | Jeng | 2001-02-23 | CLOSED
- those who passed scoring
| - those who did not pass scoring |  | None
IN-0120 | Understand "inactive" ratio, align Citibank and Associates' definitions |  |  | Jeng | N/A | WITHDRAWN - 3/13/2001 per Jeng due to change in marketing strategy
IN-0130 | Understand risk hierarchy | Report of format per Ed Eger's email of 2/16 and Jeng's email of 2/19 | None | Jeng / Telly | 2001-02-20 | CLOSED
IN-0131 | Fine-tune risk hierarchy based on first output and categorize for actions | Recommended actions of (1) close account, (2) maintain same credit line, (3) reduce credit line, (4) increase credit line | IN-0130 | Jeng | 2001-02-23 | CLOSED
IN-0132 | Augument risk hierarchy (scoring count report) to cover full customer base | Recommended actions of (1) close account, (2) maintain same credit line, (3) reduce credit line, (4) increase credit line | IN-0131, IN-0180 | Jeng | 03/02/2001 04/09/2001 | Meaningful only after new acquisition stops CLOSED - 3/19/2001
IN-0133 | Sample validate risk hierarchy output | Confirmation | IN-0131 | Jeng | 2001-03-16 | CLOSED - 03/19
IN-0134 | Determine treatment of dual relationships per guidelines: | Updated conversion criteria and actions | IN-0132 | Erica, Sam | 2001-04-09 | Weekly report to be produced until conversion starts
- Within MUE, convert
- Exceed MUE, convert and treat as test group
| - Bad performance at Citibank, close at Associates or convert depending on performance then |  | Legal
IN-0135 | Obtain approval of policy deviation for moving M1 to Citibank as current (skip one payment) | Approval | None | Jeng | 2001-03-15 | CLOSED - 3/15 - Verbal approval obtained
IN-0136 | Obtain approval in writing | Approval in writing of deviation | IN-0135 | Jeng | 2001-03-23 | CLOSED - 5/11
IN-0137 | Determine feasibility of BALCON now-M1 one month after conversion starts, only if they remain M1 or become current then | BALCON then-M1 and current | Legal, O&T capability | Jeng, Sam | 2001-03-20 | CLOSED - 03/20/2001
IN-0138 | Determine overlap period of card validity to limit double exposure risk | Acceptable risk | None | Jeng | 2001-03-15 | 3/15 - CLOSED, 7 days acceptable, aim to limit to 2 days
IN-0139 | Obtain approval in writing | Approval in writing | IN-0138 | Jeng | 2001-03-23 | CLOSED - 5/11
OPERATIONS
IN-0140 | Define absolutely necessary system changes | System requirements - BALCON support, MIS, scoring, de/activation of card | IN-0040, IN-0052 | Aftab | 2001-03-12 | CLOSED - 03/12/2001
IN-0145 | Implement absolutely necessary system changes | System ready | IN-0140 | Aftab | 04/20/01 05/20/01 06/04/01 | 3/8/2001 - Per Operations Task Force. 4/16 - revised schedule. 5/28 - revised schedule per Vincent Ku
IN-0150 | Define operational procedures to handle the conversion (not BALCON) | Procedures, risks, constraints, e.g., paper-based collection history | IN-0040 | Aftab, Esther | 2001-03-31 | 5/28 - procedures under review by QA
IN-0160 | Estimate capacity required to handle BALCON (assuming pre-approved) |  | IN-0052 | Aftab, Esther | 03/12/2001 03/23/2001 | CLOSED - 3/23
- applications (data entry)
- call center
- card embossing
- activation / inactivation
- statement rendition
- plastics stock / supply
IN-0161 | Produce customer service plan during the converion period | Call triggers, anticipated volume, time-frame, script, responses, system support, capacity |  | Daniel, Ward | ? | 5/11 - Authorization confirmed their plan. 5/16 - CLOSED
IN-0162 | Determine feasibility of ear-marking BALCON'ed amount and leave Associates accounts in use for those card accounts NOT activated | Decision |  | Christine, Jeng | 2001-03-26 | CLOSED - 3/30, flow agreed
IN-0163 | Re-work end-to-end schedule taking into consideration MOF approval and notification period | Updated schedule |  | Vincent Ku | 2001-03-26 | CLOSED - 4/3
IN-0170 | Establish common understanding and conformed execution of business processes until full integration | Process documentation | None | Functional Heads Betty | 2001-03-13 | CLOSED - 3/7/2001
- e.g., contracting 3rd-party marketing
IN-0171 | Provide update of contract review |  |  | Sam | 2001-03-13 | CLOSED - 4/16
IN-0172 | Identify contractual services to be discontinued | List of items | IN-0171 | Aftab / Christine / Mark / Weber / Rodney | 2001-03-19 | 4/3 - All except Systems had identified contracts in their area. 5/21 - CLOSED
IN-0172 IN-0173 | Identify pre-payments and collect | List of items and amount | IN-0171 | Shariq | 2001-03-26 | - APS, Vision Plus 4/3 - CLOSED
IN-0173 IN-0174 | Define and distribute FinCon guidelines | Cost centers, approval, delegation and reporting guidelines | None | Kitty | 2001-03-12 | CLOSED - 3/13/2001
IN-0180 | Address continuing new booking | Decision |  | Christine | N/A | CLOSED - 3/8/2001 - Notice given to agent
IN-0190 | Consolidate integration expenses | Expense budget | IN-0160 | Shariq Kitty | 2001-03-16 | 3/30 - CLOSED, minor adjustments expected
| - Technology |  |  | Aftab
| - Operations (fulfillment) |  |  | Aftab
| - Credit operations |  |  | Esther
| - Marketing |  |  | Christine
| - HR |  |  | Mark
| - Legal |  |  | Sam
| - Residdual processing |  |  | Rodney / Roger
IN-0191 | Determine if outstanding balance of closed accounts is to be sold | $ projection | IN-0132 | Esther / Ron | 2001-03-26 | 3/30 - WITHDRAWN, refer to IN-0192
IN-0192 | Determine collection process and system support | Decision on procedures and system |  | Esther / Ron / Alice / Aftab | 2001-04-06 | 04/09 - CLOSED. 05/08 - Re-opened. 05/16 - CLOSED, see IN-0193, IN-0194
IN-0193 | Confirm technical feasibility of manually creating non-BALCON'ed accounts into ECS | Procedures in place | None | Amy / Designate | 2001-05-23
IN-0194 | Confirm feasibility of in-sourcing arrangement | In-sourcing arrangement confirmed and in place | None | Sam | ? | CLOSED - 5/24
WK-001 | Estimate how many of M1 at "freeze" (4/23) remain M1 (5/23)? And how many M2+ today will remain M2+ but not 180-DPD by 8/31 | Project of flow from April onwards: # of accounts, $-balance | None | Theresa Liao / Ron Goodman | 2001-04-18
WK-002 | Provide breakdown of all blocked codes (especially "manual blocked" and" lost card") to shape the decision to: solicit current and M1 to BALCON, offer P-loan to M2-M4, early charge off M5-M6 | Recommendation to BALCON | None | Telly | 2001-04-17 | 4/23/ - CLOSED
WK-003 | Identify implications of 23B viz. rewrite policy, and opportunities from NCL | Process & pocedures in place, NCL opportunities | None | Theresa / Ron | 04/20/2001 05/10/2001 05/30/2001
WK-004 | Investigate why 360 customers were CitiBad but not in JCIC | Investigation report | None | Erica Lu | 2001-04-18 | 4/18 - CLOSED
WK-019 | Determine when to start RMS operation | Date | WK-001 | Ron | 2001-04-23
WK-024 | Determiine when to effect asset purchase if M2+ remain in JOCS beyond September | Date | WK-001 | Shariq, Sam |  | 4/16 - can be withdrawn once assessment made on remaining portfolio (WK-001)
WK-025 | Devise schemes to motivate collectors | Performance monitoring, incentive scheme, supervision in place - improved collection performance |  | Esther | 2001-05-01
| Understand current Associates performance and monitoring mechanism, devise incentive, help to provide supervision |  |  | Ron | 2001-05-01
| Consider advancing outsourcing from 90+DPD to 60+DPD |  |  | Ron | 2001-05-01
| Assess current capacity at Associates |  |  | Ron | 2001-05-01
| Explore early settlement program |  |  | Ron | 2001-05-30
FINCON
IN-0200 | Model financial impacts of card business | Financial model | IN-0190, IN-0172, IN-0191 | Shariq / Jesse / Vipin | 03/23/2001 04/15/2001 | 4/3 - 3rd version submitted for Regional FinCon review. 4/15 - CLOSED
| - revenue retention |  |  | Rhonda, Emerald
| - expense elimination |  |  | Rhonda, Kitty
| - NCL forecast |  |  | Vipin, Erica, Rhonda
| - EBIT impact |  |  | Rhonda
IN-0201 | Re-assess funding needs and sources |  | IN-0200, IN-0010, IN-0015, IN-0031 | Shariq, Sam, Jeannie | 2001-04-25 | CLOSED - 4/9, an OD line of NT$3.4 billion was granted on 4/9
| - Repatriate capital |  |  | Shariq, Winston | 04/25/01 09/30/01 | 5/8 - deadline extended, contingent upon decision whether to liquidate the legal vechical or not.
| - Accounting of capital |  |  | Rhonda Jeannie | 04/25/01 05/30/01 | 5/8 - need to obtain opinion from KPMG on min capital requirement
| - Funding of residual portfolio |  |  | Shariq, Winston, Alvena | 2001-04-25 | CLOSED - 4/9, same as IN-0201
WK-031 | Control physical movement of assets | Process and procedures document |  | Aftab, Eton, James, Julie, Kitty | 2001-04-18 | 4/17 - CLOSED
WK-030 | Perform AFTI financial analysis | Financial model | None | Shariq, Jim, Rodney, Kitty | 04/27/01 06/30/01 | 5/8 - deadline extended, started workshop to discuss future business model.
IN-0210 | Determine legal vehicle treatment | Decision and action plan | IN-0010 | Robert Shariq, Kitty | 2001-03-31 | 4/3 - KPMG to make recommendation by 4/4, 4/9 - CLOSED
IN-0211 | Determine treatment of goodwill | Decision and action plan | NY response | Shariq | 2001-03-31 | 3/30 - CLOSED, to be written off
IN-0212 | Functional transfer budget | Consolidated budget | Regional response (Srini) | Vipin | 04/01/01 04/30/01 06/30/01 | 5/8 - no response from Regional Office yet despite several follow-up requests.
IN-0213 | Set up accounting | Chart of accounts in FMS | None | Kitty | 2001-04-30 | CLOSED - 4/30
FINCON
IN-0220 | HR integration | HR plan | None | Mark / Maisie | ? | CLOSED - 3/15/2001
IN-0221 | Determine manpower requirement taking into consideration: | Top line headcount plan | None | Function Heads | 2001-03-21 | CLOSED - 3/23
- Associates' business support
- Citibank's ISP, e.g., Z-card
- Citibank's BAU increase
- Turnover @15%
IN-0222 | Align headcount plan with financial plan | Final headcount plan | IN-0221 | Mark / Function Heads / Shariq | 2001-03-23 | CLOSED - 3/23
IN-0223 | Obtain sign-off | Approval | IN-0222 | Robert | 2001-03-23 | CLOSED
IN-0224 | Select, offer and redeploy against approved open positions based on: | Offers made and accepted / packages | IN-0223 | HR / Line Managers | 2001-03-24 | CLOSDED - 4/17, offers made to collectors
- Job experience
- Performance
- Transferrable skills
IN-0225 | Prepare communicaton plans: | Plan to address changes, insecurity | IN-0223 | Joyce / Mark | 2001-03-23 | CLOSED - 3/23
| - Business Head overview |  |  | Joyce / Mark
| - Q&A documents |  |  | HR
| - 1-on-1 counselling |  |  | HR
IN-0226 | Induction to Citibank: | Schedule, productivity measurement | IN-0223 |  | ?
| - Orientation |  |  | HR | ? | 4/9 - Done for those who have accepted offers
| - Training |  |  | Function Heads | ?
IN-0227 | Critical staff retention | Plan | IN-0223, Regulatory
| - Department closure schedule |  |  | Rodney / Function Heads | April
| - Retention bonus |  |  | Mark | April
IN-0228 | Close existing staff cards | Accounts closed | Termination | Richie Dennis | ?
AFTI
IN-0500 | Construct / modify installment system | System in place | IN-0501, IN-0502, IN-0503 | Rick Tony Chang / Vincent Ku / Francis Yeh | September 9/10 | 4/12 - exploring ECS/EPP
IN-0501 | Submit user requirement for system changes | Signed off requirement document | None | Tony Chang | 05/16/01 05/24/01
IN-0502 | Complete system development |  | IN-0501 | Gordon Chiu | 2001-08-10
IN-0503 | Complete UAT | UAT sign-off | IN-0502 | Tony Chang / Vincent Ku / Francis Yeh | 2001-09-05 | 5/2 - Vincent to advise UAT resource requirement by 5/11
IN-0504 | Notify customers of conversion | Notification letters sent | IN-0501 | Rodney | 2001-06-15
IN-0505 | Extend HR service agreement between Citibank and AFTI | Secondment agreement in place | None | Rodney, Mark, Sam | 03/31/01 04/13/01 05/05/01 | CLOSED 5/2 - awaiting external legal counsel
IN-0510 | Amend loan contract between ACCTI and AFTI | New contract in place | None IN-0515 | David Baer Rodney, Sam | 2001-04-30
IN-0515 | Finalize legal structure | New legal structure in place | None | David Baer, Sam, Shariq | 2001-04-30 | CLOSED - 5/2, use AFTI legal vehicle, can use CitiFinancial name
IN-0520 | Finalize financial structure | New financial structure in place | None | Christina, Rhonda | 2001-04-30 | CLOSED - 5/11, full accrual reporting
IN-0525 | Assess risk management process | Risk management process in place | None | David Baer, Rodney, Jeng, Telly, Theresa | 2001-04-30 | CitiFinancial Risk Manager to visit first week in April. 04/10 - CifiFinancial visit rescheduled to April 12/13.
IN-0526 | Rerun new risk/revenue score to test relevance | Analysis report | None | Theresa | 2001-05-16
IN-0527 | Reforecast NCL | Updated NCL forecast | None | Theresa Liao / Telly Hou | 2001-05-11
IN-0530 | Further analyse applicability of credit score using 6000 credit card customers with installment loans | Credit score in place (??) | None | Jeng, Theresa, Telly, Rodney, David Baer | 2001-03-31 | 4/10 - CLOSED, output being circulated, doesn't validate
IN-0531 | Improve turnaround time and approval rate | New performance standard | IN-0530 | Johnny | 2001-04-30 | 4/10 - DELETED
IN-0535 | Devise card cross-sell program with dealers | Programs launched | Availability of system support | Rick, Sharon | ??
IN-0540 | Arrange for JCIC 7x24 access | Access rights granted |  | Hans, Telly, Johnny | 2001-03-31 | 4/10 - CLOSED
IN-0545 | Define on-going business proposition: | Business plan |  | David Baer, Rodney, Jim, David Singh, Rhonda | 2001-05-31
- Distribution channels
- Product
- Servicing
- Financial model
- Risk management
- Scoring
- System support
- MIS
- Process automation
- Target market
POST-CONVERSION
IN-0900 | Post-conversion action plans: |  |  | Jeng | 2001-09-30
| - credit limit increase for ??good guys (criteria to be determined) |  |  | Erica
| - credit limit increase + activation program for inactive accounts |  |  | Erica, Christine
| - one-month notice followed by normal collection efforts for ??bad guys (criteria to be determined) | Termination | Legal | Erica
| - Cross-sell to voluntarily attrited accounts | Credit limit increase, JCIC report | Legal opinion re: access to closed accounts | Christine
BOLD | Change since last release
Past due date or target date not confirmed

## Program Team (hidden)
Business Management (Merger Integration) | Business Management (Cards) | Business Management (Installment Finance) | O&T | Technology | Human Resources | Legal/Comm. | FinCon | Credit Operations | Project Management
Robert Matthews | Christine Teng | Jim Brown | Aftab Ahmed | James Wu | Mark Towson | Sam Hong | Shariq Mukhtar | Esther Tang | Betty Tsoi
| Rick Chen |  | Vincent Chen | Vincent Ku |  | Vita Liu | Kitty Fung | Ward Wen
Eduardo Eguren | Wen Chuang | Rodney Ichimura | Fred Fang | Jack Fu | Maisie Lam | Joyce Chen |  | Ron Goodman
|  |  | Joy Tien | Amy Lin |  | Evelyn Lin | Jesse Leung | Judy Chen
| Jeng Lee | David Baer | Dixon Hwang |  |  | Lisa Chao | Vipin Agrawal | Alice Liu
| Theresa Liao |  |  | Francis Yeh
| Erica Lu |  | Rashid Habib | EDS |  |  |  | Nic Couldrey
Rohit Gupta
| Rodney Ichimura |  |  | Gordon-K Chiu
Barry Tan
| Ed Eger |  |  | Soo-Chin Goh

## Product features (hidden)
Product features mapping |  | BOOC | Citi | Conversion strategy
|  |  |  | Active / Inactive accout | Bad account
EPP | Installment in Min Due | 10% of principle | 100% of principle |  | N/A
| Installment for reward/cash point | No | No
| How installment posting | Txn date posting | Txn date posting
| Criteria Loan cancellation by system |  | M3
Retail2EPP | Installment in Min Due | 10% of principle | 100% of principle
| Installment for reward/cash point | No | No
| How installment posting | Txn date posting | Txn date posting
| Criteria Loan cancellation by system |  | M3
ALOP | Installment in Min Due | 10% of principle | 100% of principle
| Installment for reward/cash point | No | No
| How installment posting | Txn date posting | Txn date posting
| Criteria Loan cancellation by system |  | M3
Balcon | Balcon in payment hiearchy
| Criteria Balcon cancellation by system |  | M1
Differential APR | APR - cash
| APR - retail |  |  | Offer BOOC APR for 6 months before applying Citi APR rules
| Criteria Diff. APR cancellation by system | M1 | M1
Others credit card features | Min Due | 10% new spending (retail + cash) + 2% revolving amount + fee… | 10% new retail spending + 3% (revolving amount + new cash) + RSP + installment + fee… | Follow Citi product feature.
| Late Fee | 10% of revolvling interest | By tier in outstanding amount
| Due Day | Cycle 1 -> 20 Cycle 7 -> 24 Cycle 16 -> 5 Cycle 22 -> 10 | ~ Cycle + 18/19 Cycle 1/2 -> 19 …. Cycle 25/26 -> 15
| Grace Day | Due day + 2 | Due day + 2 (??)
| Retail int. accrual | Charge int. since posting day if not full payment by next cycle | Charge int. since posting day if not full payment by next cycle
| Cash int. accrual | Charge int. since posting day if not full payment by next cycle | Daily accrual
| APR - cash | Silver/Gold: 19.71% Platinum: 14.235% Commerical Platinum: 13.88% | 20%
| APR - retail | Silver/Gold: 19.71% Platinum: 14.235% Commerical Platinum: 13.88% | 20%
| Reward / Cash rebate | Cash rebate only in next month statement | Reward or cash rebate point

## ALOP_EPP_Balcon (hidden)
ALOP
Fee
| One time upfront | By cycle | Remark
Pay by cardholder | ü |  | Principle one month defer posting
Pay by merchant
Retail to EPP
Fee
| One time upfront | By cycle | Remark
Pay by cardholder | ü | ü | Early break fee charge to "By cycle"
Pay by merchant
Mail order by EPP
Fee
| One time upfront | By cycle | Remark
Pay by cardholder
Pay by merchant | ü
NCCC EPP
Fee
| One time upfront | By cycle | Remark
Pay by cardholder |  | ü | 1. Cardholder pay only apply to MR Mall 2. Early break fee charge to "By cycle" for specific program
Pay by merchant | ü